## Sheet1
Team : Cebin, Pramod, Kiruba, Aswathy, Sowjanya,Sanjo,Siju, Jeevan
Tech Stack | Action Plans | Tasks for Prototype | Assigned To | Progress Status | Comments
Kafka Simulator |  |  |  | Target Date
| Kafka Simulator | Application of kafka producer with raw data | Sowjanya | 2 days
- Numeric
| - HL7 | Sink connector to sclylla -raw data, aggregated
Flink Streaming | Flink aggregation | Flink streaming | Sanoj
| Flink Kafka Consumer and publisher | -aggregation flink kafka consumer flink kafka publisher
Streaming Service | WebSockets | STOMP Create websocket server application | Kiruba | Websocket Server springboot done Angular consume websocket done flink, kafka,scylla docker run done
|  | configuration, broker, endpoint kafka consumer and publish topic | -
Topics : numeric raw waveform_aggregated
Query Service | REST API Controllers | Springboot REST Controller Service | Aswathy
- End points
UI Service | Angular application |  | Sijo
| consume REST Api | REST Endpoint Consumer App
| consume Streaming service | Websocket client App
Platform Deployment |  |  | Jeevan , Aswathy
Kafka
Flink
scylla
Queryservice
Streaming Service
UI Service
HL7 Models | Syclla table structure | Sijo
- pid, fromtime, totime , rawdata